## Sheet1
Change Number | Description of change | Requestor | Date | Status | Comments
CR001 | ROS cannot be used. | ROS Team | 24/02/2023 | Completed | The Radar board is not comaptable with ROS.
CR002 | Dissolve ROS Team | PM | 24/02/2023 | Completed | Because of CR001
CR003 | Not to use external data sets | S/W Team | 2023-03-03 | Completed | Data capture from Radar was successful, other data no longer required.
CR004 | Not to procure powerbank. | Stakeholder | 14/03/2023 | Completed | Cost Factor.
CR005 | Procure new Radar | H/W Team | 17/03/2023 | In progress | Current Radar H/W is not suitable to capture live data.