## Sheet1
Week No. | Milestone | Start Date | End Date
1 | Literature survey | 2023-02-06 | 2023-02-10
2 | Data capture from ImRadar sensor | 2023-02-13 | 2023-02-17
3 | Data capture from camera | 2023-02-20 | 2023-02-24
4 | Sensor axes alignment | 2023-02-27 | 2023-03-03
5 | Sensor timing synchronization | 2023-03-06 | 2023-03-10
6 | Combined data capture, compare with benchmark data (Valeo) | 2023-03-13 | 2023-03-17
7 | Final documentation | 2023-03-20 | 2023-03-24