## Extrinsic_calibration_ImR_Cam
ID | Event | Caused by (Cause) | Results in (Effect) | Description of Event | Probability | Consequence | Severity
1 | Performance Problem with ImRADAR | Communication Loss, Communication Speed on Router | Incorrect and invaluable data captured and operated upon | If these factors are not properly accounted for, the calibration could be unreliable. | 2 | 2 | 4
2 | Inaccurate Measurents | Application of non-standard procedures | Incorrect and invaluable data captured and operated upon | If these factors are not properly accounted for, the calibration could be unreliable. | 2 | 2 | 4
3 | Environmental Factors | lihgting conditions, temperature, presence of noise (unwanted) objects | Incorrect calibration | The calibration process can be affected by environmental factors such as lighting conditions, temperature. If these factors are not properly accounted for, the calibration could be unreliable. | 3 | 3 | 9
4 | Calibration Drift | Overtime change in relative positions of sensors | Incorrect calibration | Over time, the relative positions of the radar and camera can change due to factors such as vibration or thermal expansion. This can lead to calibration drift, which can cause inaccuracies in object detection and tracking. | 2 | 4 | 8
5 | Compatibility issues | ROS and Radar not compatible for use with each other | Skewed result as data capturing not completed | The camera and radar sensor may not be compatible with each other, resulting in inaccurate calibration. For example, the resolution and field of view of the camera may not match the range and resolution of the radar sensor, leading to errors in calibration. | 4 | 4 | 16
6 | Human Error | Inaccurate handling of the equipment/ usage of non-standard procedures | Equipment damage | The calibration process requires careful attention to detail and proper execution of calibration procedures. Human error, such as incorrect setup or measurement procedures, can lead to inaccurate calibration results. | 3 | 2 | 6
7 | Equipment Failure | Equipment manufacturer/shipping damages | Incorrect and invaluable data captured and operated upon | he calibration process often requires specialized equipment, such as target patterns or calibration boards. If this equipment is not functioning properly, the resulting calibration can be inaccurate. | 1 | 5 | 5
8 | Calibration method selection | Insufficient knowledge of the subject matter | Incorrect calibration | There are different methods for performing extrinsic calibration, and the choice of method can affect the accuracy of the calibration. If an inappropriate method is chosen, the resulting calibration can be inaccurate. | 2 | 5 | 10
9 | Electromagnetic interference | Caused by presence of other electronics in the vicinity of the equipment | Incorrect and invaluable data captured and operated upon | If these factors are not properly accounted for, the calibration could be unreliable. | 4 | 4 | 16

## Risks
ID | Event | Caused by (Cause) | Results in (Effect) | Description of Event | L | I | _ENC | _VAL | Response | Mitigation | Contingency
1
2 | Communication with external (outgoing) stakeholders
3 | Data is too noisy to use in the decision-making algorithm
4 | Sensor quality

## Risk Posture
L | I | _ID | Posture |  | Posture Value | Risk Reponse
0 | 0 | 0 | Resolved | Negligible | Resolved | Identified
1 | 1 | 11 | Acceptable | Minimal | Acceptable | No response required
1 | 2 | 12 | Acceptable | Minor | Tolerable | Planned
1 | 3 | 13 | Tolerable | Moderate | Undesirable | Implemented
1 | 4 | 14 | Undesirable | Major | Unacceptable | Expired
1 | 5 | 15 | Acceptable | Severe | X
2 | 1 | 21 | Acceptable
2 | 2 | 22 | Acceptable
2 | 3 | 23 | Tolerable
2 | 4 | 24 | Undesirable
2 | 5 | 25 | Acceptable
3 | 1 | 31 | Acceptable
3 | 2 | 32 | Tolerable
3 | 3 | 33 | Undesirable
3 | 4 | 34 | Undesirable
3 | 5 | 35 | Acceptable
4 | 1 | 41 | Tolerable
4 | 2 | 42 | Undesirable
4 | 3 | 43 | Undesirable
4 | 4 | 44 | Unacceptable
4 | 5 | 45 | Tolerable
5 | 1 | 51 | Undesirable
5 | 2 | 52 | Undesirable
5 | 3 | 53 | Unacceptable
5 | 4 | 54 | Unacceptable
5 | 5 | 55 | Unacceptable
1 | 75 | 85 | X

## Sheet3
Week | Acceptable | Tolerable | Undesirable | Unacceptable
1 | 2 | 1 | 4 | 5
2 | 3 | 2 | 6 | 8
3 | 5 | 1 | 5 | 7
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42