## Requirements
Sr. No. | Needs | Requirements | Validation | Priority | Source | Status
1 | Capture Sensor data from Imaging Radar and Camera | • The Sensor Database shall include captured and uncalibrated 4D point cloud data (.mat) in at least 3 different scenarios from Imaging Cascade Radar | Link for data storage on Wikipage | HIGH | Pavol | Done
|  | • The Sensor database shall include captured and uncalibrated image data (.jpg) in at least 3 different scenarios from Imaging Cascade Radar |  | HIGH |  | Done
|  | • The Sensor database shall include calibrated Radar (.mat) and image data (.jpg) in at least 3 different scenarios from Imaging Cascade Radar |  | HIGH |  | Done
2 | Extrinsically Calibrate a 4D Imaging Radar and Camera | • The Sensor Calibration System shall use MATLAB figure Post Processed data (.fig) from 4D Imaging Radar (MMWCAS-RF-EVM + MMWCAS-DSP-EVM) | Demo of Calibrated vs Uncalibrated sensor data reviewed and approved by stakeholder | MED | Pavol | Done
|  | • The Sensor Calibration System shall use image data (.jpg) from any mono camera |  | MED |  | Done
|  | • When the user wishes to input sensor data, The Sensor Calibration System shall take the folder link of the Sensor Data as input |  | MED |  | Done
|  | • when provided with raw sensor data, The Sensor Calibration System shall extract 4D Point Cloud Data in .mat format |  | MED |  | Done
|  | • when provided with raw sensor data, The Sensor Calibration System shall extract image data with RGB pixels in .mat format |  | MED |  | Done
|  | • When provided with raw sensor data, the Sensor Calibration System Shall Map Range Data from Radar with Image Data from Camera |  | HIGH |  | Done
|  | • When provided with raw sensor data, the Sensor Calibration System Shall output extrinsic calibration parameters of the Radar and Camera Sensors |  | HIGH |  | Done
|  | • When provided with raw sensor data, The Sensor Calibration System Shall Overlay Radar data on image data |  | HIGH |  | Done
|  | • When provided with raw sensor data, The Sensor Calibration System Shall Display overlayed Radar and Image data. |  | HIGH |  | Done
3 | Provide Alternate Automotive Sensor Datasets | • The Wikipage shall include at least 3 open source and calibrated automotive sensor datasets | Link for data storage on Wikipage reviewed and approved by stakeholder | MED | Pavol | In progress
4 | Document Project work | • the Project Wikipage shall have the findings, Calibration System, procedure, observations and conclusions of In-house project I | Wikipage reviewed and approved by stakeholder | MED | Pavol | Done
5 | Extrinsic Calibration System Architecture | • the Project Wikipage shall include the physical architecture of the Extrinsic Calibration System | Wikipage reviewed and approved by stakeholder | MED | Pavol | Done
6 | Market Research of Alternate Imaging Radars | • the Project Wikipage shall include at least 3 options of Imaging Radars and their specifications | Wikipage reviewed and approved by stakeholder | LOW | Pavol | in progress